Sprint 1 – Startup Manager Initiation Log Factory Inventory & Production Management System (MVP)

Document Ref: APM-SM-INITLOG-001

Version: 1.0

Owner: Nisal Wickramaarachchi (Start-up manager)

Sprint window: 09 Feb 2026 – 22 Feb 2026

Last updated: 15 Feb 2026

1. Purpose

This log records Sprint 1 project initiation activities performed by the Start-up Manager. It  provides evidence of project setup, sprint planning, governance, coordination, and  readiness for delivery.

2. Sprint Goal

Kickoff + foundations: repo/env setup, core auth + RBAC scaffolding, inventory CRUD  baseline, and initial quality & risk documentation.

3. Sprint 1 Success Criteria

• Sprint plan and backlog are created and agreed (Sprint 1 scope locked). • Repo runs locally (client + server) with env templates available.

• Authentication baseline and RBAC structure are ready for iteration. • Inventory CRUD baseline is demoable (basic end-to-end flow).

• Risk plan/log and Quality plan/log are created and stored in Drive. • Sprint Review is planned with a demo script and checklist.

4. Kickoff Checklist (Completed)

Item Status Notes

Project folder structure  created in Drive

Done Drive organised into:  Project Plan, Sprint

Planning, Risk, Quality,

Minutes, Startup Manager

Template documents  collected

Roles confirmed and  owners assigned

Done Project Plan template +  Comms template + minutes

stored

Done PM, Start-up, Scheduling,  Quality, Risk roles

confirmed

Backlog baseline created Done Product backlog drafted  with MoSCoW + story

points (initial estimates)

Sprint 1 scope drafted Done Sprint goal + Sprint 1 tasks  drafted; Sprint 2–4

placeholder created

Definition of Done agreed  (high-level)

Done AC met, review, lint/tests  pass, docs updated, demo

ready

Tooling ready Done Git repo, Node/NPM scripts,  env placeholders, basic

runbook

Comms plan drafted Done Cadence: daily sync, weekly  risk, mid-sprint quality

checkpoint, end-sprint

review/retro

5. Initialization Decisions (Sprint 1)

Decision ID Decision Reason Status

D-01 Use Firebase  Email/Password for

authentication

D-02 Enforce RBAC  server-side

(middleware)

D-03 Use MongoDB Atlas;  enable replica set if

transactions needed

Fast MVP auth,  managed security

Prevent UI-only  security

Supports cloud  hosting + optional  transactions

Approved Approved Pending

D-04 Adopt FEFO for  dispatch allocation

in later sprints

Reduce expiry waste Approved

6. Documents and Artefacts Created (Drive Evidence) Artefact Status Notes

Sprint Planning workbook  (4 sprints)

Risk Management Plan +  Risk Register

Quality Plan + Quality Log  (Sprint 1)

Project Plan (updated to  include all roles)

Communication Plan

(completed)

Startup Manager pack (draft  evidence set)

Created and uploaded Sprint 1 filled; Sprint 2–4  placeholders

Created and uploaded Owners + mitigations  tracked

Created and uploaded DoD + QA checks + log  entries

Created and uploaded Brief 4-sprint plan included

Created and uploaded Stakeholders + cadence +  approvals table

Created and uploaded Vision + roadmap +  templates

7. Dependencies and Issues Log (Startup Manager View) Ref Type Description Impact Mitigation /  Action

Status

DI-01 Dependency Firebase project  credentials

availability

(Email/Password

enabled)

DI-02 Issue CORS allowlist  and Vercel

routing for

nested API paths

may block demo

Medium Ensure env  keys are

available early;

validate

formatting (\n

in private key).

High Confirm  vercel.json

routing and

app.options('*')

for preflight;

test /api/*

Open Open

DI-03 Dependency MongoDB Atlas  cluster

configuration

(replica set for

transactions)

DI-04 Issue Test coverage  baseline still

minimal

endpoints.

High If transactions  fail, adjust

implementation

or upgrade

cluster settings.

Medium Prioritise  smoke tests for

login +

inventory

CRUD; add CI

later.

Open

In Progress

8. Communication Log (Startup Manager)

Ref Communication Audience Summary Status

COM-01 Kickoff  coordination

message

COM-02 Sprint 1 scope  summary

Team Drive structure  + sprint plan

location shared

PM + Team Sprint goal +  initial backlog +

responsibilities

Sent Sent

COM-03 Quality/Risk  artefact links

Quality + Risk  managers

Shared

templates +  logs for updates

Sent

COM-04 Sprint Review  preparation

9. 4-Sprint Plan (Brief)

Team Demo script  checklist +

agenda

Planned

Sprint Theme Key planned outcomes

Sprint 1 Kickoff + foundations Repo/env, auth+RBAC  baseline, inventory CRUD

baseline, risk+quality

artefacts

Sprint 2 Ledger + batches + FEFO  base

Sprint 3 Orders + dispatch + PDF +  audit

Stock ledger, receiving,  batch tracking, FEFO  selection logic + tests

Orders flow, dispatch  consumes FEFO, delivery note PDF, stronger audit  trail

Sprint 4 Hardening + deploy + polish Deployment guide,  validation/rate-limits, UI

polish, final demo assets

10. Next Actions (Sprint 1 Continuation)

• Run Sprint 1 mid-sprint checkpoint: confirm progress vs sprint goal and update  blockers.

• Align with Scheduling manager to ensure sprint events (review/retro) are booked and  minutes shared.

• Confirm Firebase + MongoDB envs for stable demo environment. • Coordinate with Quality manager to finalise DoD checklist per story and expand smoke  tests.

• Coordinate with Risk manager to update top risks and mitigation status before review.

11. Sign-off

Prepared by: Nisal Wickramaarachchi

Role: Start-up manager